## Overview
Project | B2B Marketplace Platform
Scope | Phases 2 to 6
Phases included | 2 Authentication, 3 Buyer Dashboard, 4 Supplier Dashboard, 5 Payments & Credits, 6 Admin Panel
Users | Buyer, Supplier, Admin
Final delivery date | 26 June 2026

## Modules & Features
Phase | Module | Feature
2 | Authentication & Onboarding | Login (email & password)
2 | Authentication & Onboarding | Buyer registration
2 | Authentication & Onboarding | Supplier registration (multi-step)
2 | Authentication & Onboarding | Google single sign-on
2 | Authentication & Onboarding | Forgot / reset password
2 | Authentication & Onboarding | Phone OTP verification
2 | Authentication & Onboarding | User roles & protected areas
3 | Buyer Dashboard | Dashboard overview
3 | Buyer Dashboard | Post RFQ
3 | Buyer Dashboard | Manage RFQs (edit / close / delete)
3 | Buyer Dashboard | Receive & accept / reject quotations
3 | Buyer Dashboard | Saved suppliers / products / RFQs
3 | Buyer Dashboard | Notifications & preferences
3 | Buyer Dashboard | Profile settings & change password
4 | Supplier Dashboard | Dashboard overview
4 | Supplier Dashboard | Browse RFQ feed
4 | Supplier Dashboard | Submit & withdraw quotations
4 | Supplier Dashboard | Product management (add / edit / delete)
4 | Supplier Dashboard | Company profile & trade terms
4 | Supplier Dashboard | Verification (document submission)
4 | Supplier Dashboard | Profile settings & change password
5 | Payments & Credits | Credit packs
5 | Payments & Credits | Buy credits (Stripe checkout)
5 | Payments & Credits | Payment webhook & credit grant
5 | Payments & Credits | Credit ledger / transaction history
5 | Payments & Credits | Unlock supplier contacts
6 | Admin Panel | Admin dashboard (stats & activity)
6 | Admin Panel | User management (approve / block)
6 | Admin Panel | Impersonate user login
6 | Admin Panel | Supplier verification queue
6 | Admin Panel | Document review (approve / reject)
6 | Admin Panel | RFQ moderation (flag / delete)
6 | Admin Panel | Category management
6 | Admin Panel | CMS page management
6 | Admin Panel | FAQ management
6 | Admin Panel | Credit / token management
6 | Admin Panel | Audit logging

## Technology Stack
Area | Technology | Purpose
Framework | Next.js / React | SEO-friendly server rendering; full-stack app
Language | TypeScript | Type safety across the application
Database | PostgreSQL | Relational data for users, RFQs, quotes, credits
ORM | Prisma | Type-safe database access & migrations
Authentication | Auth.js (NextAuth) | Email, Google SSO, roles, impersonation
Validation | Zod | Client & server input validation
UI / Styling | Tailwind CSS + shadcn/ui | Modern, accessible interface
Payments | Stripe | Secure credit-pack checkout
Email | Resend | Transactional email
SMS / WhatsApp | Twilio | Phone verification & alerts
Messaging | Telegram Bot API | Opt-in notifications
File Storage | Cloudflare R2 / S3 | Documents & media
Hosting | Any Node.js host | Railway / Render / DigitalOcean / AWS / VPS
Database Hosting | Managed PostgreSQL | Scalable managed database

## Development Phases
Phase | Module | Key Deliverables
2 | Authentication & Onboarding | Login, registration, Google SSO, supplier onboarding, password reset
3 | Buyer Dashboard | RFQs, quotations, saved items, notifications, profile
4 | Supplier Dashboard | RFQ feed, quotations, product management, company profile, verification
5 | Payments & Credits | Credit packs, Stripe checkout, payment webhook, credit ledger, unlock contacts
6 | Admin Panel | User management, verification, moderation, CMS, FAQ, categories, credits, audit
Final delivery date |  | 26 June 2026